## Sheet1
Task Name | Assigne To | Percentage Of Work Status |  | Status | Est Time
Creating a meeting 2types Urgent and Regular | Anuj | 100% done |  | Completed
Accessibility Entire app by CEO, and meeting with Host resting allowing who can (participation rights) with CEO/Host | Anuj | 100% done |  | Completed
Logins and its confirmations by CEO/HOST | Anuj | 100% done |  | Completed
Creating Multiple meetings (Overview available on Dash board) | Anuj | 100% done |  | Completed
Text Chat box | Anuj, Danish and Nitesh | 50% done | Dev Is Completed Integration Is pending | In-Progress | 7 Days
File sharing | Danish | 30% done | Only sharable to localhost, creting issue with other IP | In-Progress | 10 Days
Audio Calling (Multiple Joining) | Nitesh | 40% done | Dev is not completed yet | In-Progress | 10 Days
Video Calling (Multiple Joining) | Nitesh | 50% done | Dev Is Completed Integration Is pending | In-Progress | 7 Days
Polling | Anuj | 100% done |  | Completed
Final comments of meeting | Anuj | 0% done |  | Not-Started | 5 Days
Preparation of MOM | Susmita | 0% done |  | Not-Started | 7 Days
Sharing MOM with All by mail | Susmita | 0% done |  | Not-Started | 4 Days
Followup Scheduling and its reminder | Anuj | 40% done |  | In-Progress | 7 Days
Conclusion of meeting before it is removed from the Dash board | Anuj | 10% done |  | In-Progress | 7 Days
Backend API and Database | Danish | 40% done | Continuing along with field requirements | In-Progress | 20 Days
UI development | Anuj and Susmita | 60% done | All user screens are ready will have to prepare for screens of chat and Video conferencing | In-Progress | 12 Days
`
|  |  |  | Total Estimated Time | 30 Working Days
Completed
In Progress
Not Started

## Danish
Task Name | Assigne To | Percentage Of Work Status |  | Status | Est Time | Task Description
Text Chat box | Danish | 50% done | Dev Is Completed Integration Is pending | In-Progress | 7 Days | Coding,Integration
File sharing | Danish | 30% done | Only sharable to localhost, creting issue with other IP | In-Progress | 10 Days | Coding,Integration
Backend API and Database | Danish | 40% done | Continuing along with field requirements | In-Progress | 20 Days | Coding,Integration
|  |  |  | Total Estimated Time | 37 Days

## Nitesh
Task Name | Assigne To | Percentage Of Work Status |  | Status | Est Time | Expaned Time after estimation | Task Description
Audio Calling (Multiple Joining) | Nitesh | 40% done | Dev is not completed yet | In-Progress | 10 Days | 2 days - Development is done ,I need to test proper way on SIT as well Integration Is pending | Create Sepearte Application for Audio call in MVC and in this integrate Twalio dll for audio conf call so multiple user are able to join the call on same time.It's just a paid number so when any one call that no on meeting time then automally recive the call and User are able to speak and Listen clearly
Video Calling (Multiple Joining) | Nitesh | 50% done | Dev Is Completed Integration Is pending | In-Progress | 7 Days |  | Develop Seperate App using MVC and SignalR for Video conf and when we click the video option then it's automatically reconize device in our system and on so everyone are able to see the video so same time 50 user are able to join the call
Text Chat box | Nitesh | 50% done | Dev Is Completed Integration Is pending | In-Progress | 7 Days |  | Develop sepearte App for chat so suppose 50 user are availavle on metting and any one want's to write anything then they need to click chat option and one popup show then need to input Name and connct so eveyone are able to understnd who are sinding this message and who are replying
|  |  |  | Total Estimated Time | 24 Days

## Anuj
Task Name | Assigne To | Percentage Of Work Status | Task Description | Status | Est Time
Creating a meeting 2types Urgent and Regular | Anuj | 100% done |  | Completed
Accessibility Entire app by CEO, and meeting with Host resting allowing who can (participation rights) with CEO/Host | Anuj | 100% done |  | Completed
Logins and its confirmations by CEO/HOST | Anuj | 100% done |  | Completed
Polling System | Anuj | 100% done |  | Completed
Text Chat Box | Anuj | 50% done | Have to develop the UI in frontend and link with the all the user, so that only meeting participants can chat in between | In-Progress | 7 Days
Creating Multiple meetings (Overview available on Dash board) | Anuj | 100% done |  | Completed
Followup Scheduling and its reminder | Anuj | 40% done | Need to complete the mailing whenever if the meeting is scheduled today. | In-Progress | 7 Days
Conclusion of meeting before it is removed from the Dash board | Anuj | 100% done | Need to implement the conclusion only when user is host or super admin and only when the meeting is completed. Also have to give permission to user to delete the meeting or not. | Completed
UI development | Anuj and Susmita | 60% done | All user screens are ready will have to prepare for screens of chat and Video conferencing | In-Progress | 10 Days
|  |  |  | Total Estimated Time | 24 Days

## Susmita
Task Name | Assigne To | Percentage Of Work Status | Status | Est Time | Task Description
Preparation of MOM | Susmita | 40% done | In-progress | 5 Days | Have to prepare multiple user inputs so that user will update MOM at any time and and add number of points which can be stored in array in backend and show them here in list format. Also only host will update this MOM
Sharing MOM with All by mail | Susmita | 0% done | Not-Started | 4 Days | When the meeting status is completed then only shows a button of send MOM by mail which will send mail to all the participants of the meeting.
Polling | Susmita | 100% done | Completed
UI development | Susmita and Anuj | 60% done | In-Progress | 10days | All user screens are ready will have to prepare for screens of chat and Video conferencing
|  |  | Total Estimated Time | 19 Days